## projectnaam
| project: WBS Monitor | [5 empty] | datum:
calculator: Benjamin Porobic
nr | onderdeel | eis (MoSCoW) | ontwikkelaar | mogelijk risico | tijd (plan) | tijd (do) | evaluatie (check) | leermoment (act)
1 | Tasks verwijderen | S | Damien |  | 1.5
2 | Tasks timer | M | Damien |  | 1 | 1
3 | Tasks update values | M | Kevin & Damien | Automatish opslaan of via save button | 3.5
4 | Tasks toevoegen | M | Jake |  | 1.5
5 | Tasks - totalen uitrekenen | M | Damien |  | 1.5
6 | Layout overhaul | S | Kevin |  | 5
7 | Login | C | Kevin |  | 2
8 | Task page- show project name | S | Kevin |  | 1
9 | When removing a project: remove all associated tasks | S | Jake |  | 0.5
10 | Project creator can share projects to other users. | C | Jake |  | 3
11 | Project Creator can remove projects | S | Jake |  | 0.5
12 | Project Creator can remove tasks | S | Jake |  | 0.5
13 | Check if you can add unlimited Projects | M | Jake |  | 0.25
14 | Check if you can add unlimited Tasks | M | Jake |  | 0.25
15 | ERD | M | Kevin |  | 0.5
16 | Responsive maintenance | M | Kevin |  | 3.5
17 | Clean up code, make code efficient | M | Jake |  | 0.5
18 | Clean up file structure, orginize files | M | Jake |  | 0.5
19 | Form validation | S | Kevin |  | 2
20 | User feedback (messages) | S | Kevin |  | 0.5
21 | If plan > do Give a red color | S | Damien |  | 0.5
22 | If total plan > do Give color | S | Damien |  | 0.5
23 | Test website (different browsers) | S | All |  | 3
24 | Database maintenance | S | Jake |  | 0.5
| totaal |  |  |  | 34 | 1
1,5 = ander half uur
Dus niet 1 uur en 5 min

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).